## README
Enterprise Application Sustainment & UAT Lab
Project Purpose
Simulated portfolio project demonstrating business requirements documentation, reporting, data analysis, application testing, issue investigation, user documentation, and continuous-improvement support.
All users, requirements, issues, test cases, and operational data are simulated. No employer or production data is used.
Workbook components:
1. Requirements Register — business needs, acceptance criteria, priority, owner, and traceability.
2. UAT Test Cases — test steps, expected results, actual results, status, and linked requirements.
3. Issue Log — simulated application issues, severity, root cause, resolution, and status.
4. Change Tracker — enhancement/change requests with impact, testing, communication, and implementation status.
5. User Documentation — job aids/reference guides and audience/status tracking.
6. Dashboard — requirement, UAT, issue, and change KPIs with charts.
7. Process Map — simple sustainment lifecycle from request through implementation and documentation.

## Requirements Register
Business Requirements Register
Req ID | Business Area | Requirement | Business Value | Priority | Acceptance Criteria | Owner | Status | Linked Test | Change ID | Notes
REQ-001 | Field Operations | Allow supervisors to filter work orders by crew and due date | Faster daily planning | High | Filter returns only selected crew/date range | Operations Lead | Approved | UAT-001 | CHG-001 | Simulated
REQ-002 | Field Operations | Display overdue work prominently | Improve prioritization | High | Overdue work is visually identifiable | Operations Lead | Approved | UAT-002 | CHG-001 | Simulated
REQ-003 | Scheduling | Export weekly work summary to CSV | Reduce manual reporting | Medium | CSV contains required fields and correct totals | Scheduler | In Testing | UAT-003 | CHG-002 | Simulated
REQ-004 | User Support | Add clearer error message for failed work-order sync | Reduce support calls | Medium | User receives actionable error text | Support Lead | Approved | UAT-004 | CHG-003 | Simulated
REQ-005 | Reporting | Create completion-rate KPI by district | Improve operational visibility | High | Dashboard calculates completion rate by district | Reporting Analyst | In Testing | UAT-005 | CHG-004 | Simulated
REQ-006 | Training | Create quick-reference guide for new workflow | Improve adoption | Medium | Guide covers login, search, update, and escalation | Training Lead | Draft | UAT-006 | CHG-001 | Simulated
REQ-007 | Data Quality | Prevent blank completion codes | Improve data integrity | High | Save blocked when completion code is blank | Business Analyst | Approved | UAT-007 | CHG-005 | Simulated
REQ-008 | Field Operations | Preserve user filter between sessions | Reduce repetitive setup | Low | Last valid filter loads on next login | Operations Lead | Backlog | UAT-008 | CHG-006 | Simulated

## UAT Test Cases
User Acceptance Testing Matrix
Test ID | Req ID | Scenario | Precondition | Test Steps | Expected Result | Actual Result | Status | Tester | Test Date | Defect ID | Evidence
UAT-001 | REQ-001 | Validate REQ-001 business outcome | Test user and sample work records available | 1. Open application 2. Complete workflow 3. Compare result to acceptance criteria | Filter returns only selected crew/date range | Matches expected result | Pass | Navid Rahman | 2027-03-04 |  | Screenshot / notes (simulated)
UAT-002 | REQ-002 | Validate REQ-002 business outcome | Test user and sample work records available | 1. Open application 2. Complete workflow 3. Compare result to acceptance criteria | Overdue work is visually identifiable | Matches expected result | Pass | Navid Rahman | 2027-03-05 |  | Screenshot / notes (simulated)
UAT-003 | REQ-003 | Validate REQ-003 business outcome | Test user and sample work records available | 1. Open application 2. Complete workflow 3. Compare result to acceptance criteria | CSV contains required fields and correct totals | Matches expected result | Pass | Navid Rahman | 2027-03-06 |  | Screenshot / notes (simulated)
UAT-004 | REQ-004 | Validate REQ-004 business outcome | Test user and sample work records available | 1. Open application 2. Complete workflow 3. Compare result to acceptance criteria | User receives actionable error text | Matches expected result | Pass | Navid Rahman | 2027-03-07 |  | Screenshot / notes (simulated)
UAT-005 | REQ-005 | Validate REQ-005 business outcome | Test user and sample work records available | 1. Open application 2. Complete workflow 3. Compare result to acceptance criteria | Dashboard calculates completion rate by district | Validation failed; issue logged | Fail | Navid Rahman | 2027-03-08 | ISS-005 | Screenshot / notes (simulated)
UAT-006 | REQ-006 | Validate REQ-006 business outcome | Test user and sample work records available | 1. Open application 2. Complete workflow 3. Compare result to acceptance criteria | Guide covers login, search, update, and escalation | Blocked by dependent fix | Blocked | Navid Rahman | 2027-03-09 | ISS-006 | Screenshot / notes (simulated)
UAT-007 | REQ-007 | Validate REQ-007 business outcome | Test user and sample work records available | 1. Open application 2. Complete workflow 3. Compare result to acceptance criteria | Save blocked when completion code is blank | Matches expected result | Pass | Navid Rahman | 2027-03-10 |  | Screenshot / notes (simulated)
UAT-008 | REQ-008 | Validate REQ-008 business outcome | Test user and sample work records available | 1. Open application 2. Complete workflow 3. Compare result to acceptance criteria | Last valid filter loads on next login | Matches expected result | Pass | Navid Rahman | 2027-03-11 |  | Screenshot / notes (simulated)

## Issue Log
Application Sustainment Issue Log
Issue ID | Opened | Source | Category | Severity | Description | Business Impact | Root Cause | Resolution | Status | Owner | Days Open
ISS-001 | 2027-03-13 | End User | Application Error | Low | Simulated application error issue affecting enterprise application workflow | Workflow interruption | Configuration | Fix validated and documented | Resolved | Support Team | 5
ISS-002 | 2027-02-13 | End User | Sync | Medium | Simulated sync issue affecting enterprise application workflow | Reporting accuracy risk | Permission | Fix validated and documented | Resolved | Systems Team | 5
ISS-003 | 2027-03-10 | UAT | Data Quality | Low | Simulated data quality issue affecting enterprise application workflow | Reporting accuracy risk | Configuration | Fix validated and documented | Resolved | Systems Team | 1
ISS-004 | 2027-03-11 | Project Review | Sync | High | Simulated sync issue affecting enterprise application workflow | Reporting accuracy risk | Configuration | Fix validated and documented | Resolved | Business Analyst | 4
ISS-005 | 2027-02-10 | UAT | Application Error | High | Simulated application error issue affecting enterprise application workflow | Multiple users affected | Integration | Fix validated and documented | Resolved | Support Team | 6
ISS-006 | 2027-02-22 | Monitoring | Performance | Medium | Simulated performance issue affecting enterprise application workflow | Reporting accuracy risk | Data Mapping | Fix validated and documented | Resolved | Reporting Team | 5
ISS-007 | 2027-03-03 | Project Review | Data Quality | High | Simulated data quality issue affecting enterprise application workflow | Workflow interruption | Integration | Investigation in progress | In Progress | Reporting Team | 8
ISS-008 | 2027-03-05 | UAT | Performance | Medium | Simulated performance issue affecting enterprise application workflow | Multiple users affected | Integration | Investigation in progress | In Progress | Business Analyst | 2
ISS-009 | 2027-03-11 | End User | Access | High | Simulated access issue affecting enterprise application workflow | Workflow interruption | Unknown | Fix validated and documented | Resolved | Business Analyst | 3
ISS-010 | 2027-03-05 | UAT | Data Quality | Medium | Simulated data quality issue affecting enterprise application workflow | Multiple users affected | Unknown | Fix validated and documented | Resolved | Systems Team | 5
ISS-011 | 2027-02-15 | Monitoring | Sync | Low | Simulated sync issue affecting enterprise application workflow | Minor user delay | Unknown | Fix validated and documented | Resolved | Support Team | 3
ISS-012 | 2027-02-08 | UAT | Data Quality | High | Simulated data quality issue affecting enterprise application workflow | Reporting accuracy risk | Data Mapping | Fix validated and documented | Resolved | Reporting Team | 6
ISS-013 | 2027-02-22 | End User | Access | Medium | Simulated access issue affecting enterprise application workflow | Multiple users affected | Validation Gap | Fix validated and documented | Resolved | Reporting Team | 6
ISS-014 | 2027-03-01 | Project Review | Performance | Medium | Simulated performance issue affecting enterprise application workflow | Reporting accuracy risk | Integration | Fix validated and documented | Resolved | Business Analyst | 4
ISS-015 | 2027-02-28 | End User | Reporting | High | Simulated reporting issue affecting enterprise application workflow | Reporting accuracy risk | Unknown | Fix validated and documented | Resolved | Reporting Team | 3
ISS-016 | 2027-03-03 | UAT | Application Error | Medium | Simulated application error issue affecting enterprise application workflow | Minor user delay | Unknown | Fix validated and documented | Resolved | Systems Team | 3
ISS-017 | 2027-03-12 | End User | Performance | High | Simulated performance issue affecting enterprise application workflow | Multiple users affected | Permission | Fix validated and documented | Resolved | Reporting Team | 4
ISS-018 | 2027-03-04 | End User | Application Error | Medium | Simulated application error issue affecting enterprise application workflow | Reporting accuracy risk | Integration | Fix validated and documented | Resolved | Reporting Team | 1
ISS-019 | 2027-03-08 | Project Review | Reporting | Low | Simulated reporting issue affecting enterprise application workflow | Reporting accuracy risk | Data Mapping | Fix validated and documented | Resolved | Support Team | 3
ISS-020 | 2027-02-25 | UAT | Application Error | High | Simulated application error issue affecting enterprise application workflow | Reporting accuracy risk | Permission | Pending triage | Open | Business Analyst | 10
ISS-021 | 2027-03-10 | Project Review | Reporting | High | Simulated reporting issue affecting enterprise application workflow | Reporting accuracy risk | Permission | Fix validated and documented | Resolved | Business Analyst | 3
ISS-022 | 2027-02-07 | Project Review | Reporting | Low | Simulated reporting issue affecting enterprise application workflow | Minor user delay | Validation Gap | Investigation in progress | In Progress | Systems Team | 7
ISS-023 | 2027-02-03 | Monitoring | Data Quality | Medium | Simulated data quality issue affecting enterprise application workflow | Workflow interruption | Integration | Fix validated and documented | Resolved | Business Analyst | 5
ISS-024 | 2027-02-17 | End User | Data Quality | Medium | Simulated data quality issue affecting enterprise application workflow | Workflow interruption | Data Mapping | Fix validated and documented | Resolved | Reporting Team | 6
ISS-025 | 2027-03-10 | Project Review | Application Error | Medium | Simulated application error issue affecting enterprise application workflow | Multiple users affected | Integration | Fix validated and documented | Resolved | Systems Team | 6

## Change Tracker
System Enhancement & Change Tracker
Change ID | Title | Linked Req | Impact | Risk | Test Status | Communication | Implementation | Rollback | Owner | Status
CHG-001 | Field workflow usability update | REQ-001; REQ-002; REQ-006 | Field supervisors and users | Medium | Pass | Job aid + team notice | 2027-03-15 | Restore prior configuration | Systems Team | Ready
CHG-002 | Weekly report export | REQ-003 | Schedulers | Low | In Testing | Release note | 2027-03-20 | Disable export option | Reporting Team | Testing
CHG-003 | Sync error messaging | REQ-004 | All field users | Low | Pass | KB update | 2027-03-18 | Restore previous message | Support Team | Ready
CHG-004 | District completion KPI | REQ-005 | Operations managers | Medium | In Testing | Dashboard note | 2027-03-22 | Hide new KPI | Reporting Team | Testing
CHG-005 | Completion-code validation | REQ-007 | Field users / reporting | High | Pass | Training note | 2027-03-16 | Disable validation rule | Systems Team | Ready
CHG-006 | Persistent user filters | REQ-008 | Field users | Low | Not Started | TBD | TBD | TBD | Systems Team | Backlog

## User Documentation
User Documentation & Training Tracker
Doc ID | Document | Audience | Purpose | Owner | Status | Last Updated | Linked Change
DOC-001 | Field Work Search Quick Guide | Field users | Explain search/filter workflow | Business Analyst | Complete | 2027-03-10 | CHG-001
DOC-002 | Supervisor Daily Planning Job Aid | Supervisors | Summarize filtering and overdue work | Business Analyst | Complete | 2027-03-11 | CHG-001
DOC-003 | Weekly Export Reference | Schedulers | Explain report export and validation | Reporting Analyst | Draft | 2027-03-12 | CHG-002
DOC-004 | Sync Error Troubleshooting Guide | End users / support | Explain user steps and escalation | Support Lead | Complete | 2027-03-12 | CHG-003
DOC-005 | Completion KPI Definition | Operations managers | Define metric and interpretation | Reporting Analyst | Review | 2027-03-13 | CHG-004
DOC-006 | Completion Code Validation Notice | Field users | Explain new required field | Business Analyst | Complete | 2027-03-13 | CHG-005

## Process Map
Enterprise Application Sustainment Lifecycle
1. Request / Issue Capture Business need, user issue, or improvement idea | 2. Analyze / Document Requirements, impact, priority, acceptance criteria | 3. Test / Validate UAT, defect logging, results and evidence | 4. Implement / Coordinate Change, communication, rollback and release | 5. Sustain / Improve Issue resolution, reporting, job aids and lessons learned
Traceability principle: each approved business requirement links to a UAT case and, where applicable, a change record. Failed tests create issues that are investigated, resolved, re-tested, and documented before release.

## Dashboard
DX Sustainment / UAT Dashboard — Simulated
Requirements |  | Approved / Testing |  |  | UAT Pass Rate | Open Issues
8 |  | 6 |  |  | 75% | 4
High/Critical Issues |  | Resolved Issues |  |  | Changes Ready | Docs Complete
9 |  | 21 |  |  | 3 | 4
Issue Category | Count |  | UAT Status | Count
Data Quality | 6 |  | Pass | 6
Application Error | 6 |  | Fail | 1
Access | 2 |  | Blocked | 1
Reporting | 4
Sync | 3
Performance | 4
Portfolio Note
This project uses simulated enterprise-application data to demonstrate requirements traceability, UAT, reporting, issue investigation, change coordination, user documentation, and continuous improvement.